## Deramakot FMU 19A
QUARTERLY PROGRESS REPORT 2023 (2nd)
DERAMAKOT - FMU 19A
NO. | ACTIVITIES | LOCATION / | TARGET |  | ACHIEVEMENT |  |  |  |  | PERCENT | REMARKS
|  | Compt/Block | (ha) | (Species) | QR-1 | QR-2 | QR-3 | QR-4 | TOTAL | (%)
1 | REDUCED IMPACT LOGGING
| A) CHP Planning | CPT 105 | 531.7 |  | 0 | 0 |  |  | 0 | 0% | Area reconnaissance and markings ongoing.
|  | MR 1 | 56 |  | 56 | n/a |  |  | 56 | 100% | Done
|  |  | 587.7 |  | 56 | 0 | 0 |  | 56 | 9.529% | Personnel incapacity.
| B) Harvesting | Cpt 66A | 238 |  | 2.38 | 27.39 |  |  | 29.77 | 12.51% | 404 trees felled to date/328 trees felled during qr 2/approx. 3,030m3
|  | Cpt 66B | 189 |  | 0 | 0 |  |  | 0 | 0% | Felling focused in cpt 66A to date.
|  | MR 2 | 120 |  | 0 | 0 |  |  | 0 | 0% | Felling focused in cpt 66A to date.
|  | SR Tabalion | 7.23 |  | 7.23 | n/a |  |  | 7.23 | 100% | Done. 51 trees felled (tumbang matahari). AWP will be revised to incorporate Secondary Road Tabalion tumbang matahari activity.
|  |  | 554.23 |  | 9.61 |  |  |  | 37 | 6.676% | Felling commenced late february after RIL course towards th contractor. Other factor was the wet condition prior. Poor performance by the new contractor : To date there is only 1 harvesting team available as opposed to the supposed 5.
| C) Post Harvest | Cpt 66A | 238 |  | 0 |  |  |  | 0 | 0% | Yet to be done
|  | Cpt 66B | 189 |  | 0 |  |  |  | 0 | 0% | Yet to be done
|  |  | 427 |  | 0 |  |  |  | 0 | 0% | Await harvesting conclusion in cpt 66
| D) Log Auction |  | 2x |  | 0 |  |  |  | 0 | 0%
1st auction to be done when all logs reached Sapa Payau stumping with Projadi being given ultimatum it has to do so before 07.08.2023..
2 | FSC Re-assessment | Pre-assesment | 1 |  | 1 |  |  |  | 1 | 100% | Done
|  | Main-assessment | 1 |  | 0 |  |  |  | 0 | 0% | Scheduled to be done end of QR 3.
|  | Certificate issuance | 1 |  | 0 |  |  |  | 0 | 0% | Yet to be done
Appointed Certification Body is Preferred By Nature. Effort is underway to have the main-assessment done within at least QR 3.
3 | TIMBER STAND IMPROVEMENT (SILVICULTURE TREATMENT) | Cpt 126 | 525.6 |  | 525.6 | n/a |  |  | 525.6 | 100% | Done
|  | Cpt 127 | 463.9 |  | 0 | 463.9 |  |  | 463.9 | 100% | Done
| TOTAL |  | 989.5 |  | 525.6 | 463.9 | 0 |  | 989.5 | 100% | Done
4 | Restoration (Planting & Maintenance) | Cpt 108 | 100ha (EU) | 1x sporadic maintenance only on infilled trees since 2016 | 0 | 53 |  |  | 53 |  | Ongoing.
|  |  | 25ha (PPM) |  | 0.7ha | 0 |  |  | 0.7 |  |  | 0.7
[5 empty] | 0.7 | 53 |  |  | 53.7 |  | This is as and when necessary only.
FOREST PROTECTION (As per HCV and protection plan)
5 | A) Patrolling/Surveillance/monitoring | Ground Patrol | at least 500km/month |  | 1987.34 | 2920 |  |  | 4907.34 | 81.79% | Continuous. This is by DFR's Wildlife Unit and enforcement. Apart from that, there's weekend patrol by group rotation consisting of all DFR staff. HCV entity of cpt 108 intact. No forest offenses were detected. Inclusiive of 48km patrolling on foot.
|  | River Patrol | at least 100km/month |  | 486.76 | 2326 |  |  | 2812.76 | 234.4% | Continuous. This is by Protection Unit stationed in Balat. No Forest offence detected.
|  | Aerial patrol | 3X |  | 1 | 1 |  |  | 2 | 66.67% | Along boundary and inland HCV entities as well as along main rivers that are inaccessible by road. Entities are intact. No forest offenses were detected.
No offenes detected during qr 2.
| B) Boundary Maintenance (Common Boundary, Conservation Area, HCVF) -Social Forestry Community. |  | Sg Tabalion - Sg. Deramakot | 21km | 0 | 21 |  |  | 21 | 99.72% | Contracted out to Balat communities.
|  |  | Sg. Karis-karis - Sg rago rago | 12 km | 0 | 12 |  |  | 12 | 84.21% | Contracted out to Desa Permai communities
|  |  | Sg. Deramakot - Sg. Karis Karis | 20.5km | 0 | 20.5 |  |  | 20.5 | 145.9% | Contracted out to Kuamut communities
|  |  | Sg Rago Rago - Sg Tangkulap Kecil | 17.6km | 0 | 17.6 |  |  | 17.6 | 100% | Contracted out to Kg. Tulang Tulang communities.
| TOTAL |  |  | 71.1 | 0 | 71.1 | 0 | 0 | 71.1 | 100% | Done.
| WILDLIFE MANAGEMENT | Opportunistic Sightings | Continuous |  | Continuous | Continuous |  |  |  |  | Continuous. Analysis by year end.
6 |  | Orang Utan Census | 1x |  | 0 | 0 |  |  | 0 | 0% | A census will be done this year and is expected to be done in QR 3.
|  | Camera Traps (Cpt 63,72,71 & 49) | 12x |  | 3 | 3 |  |  | 6 | 50% | Data collection done monthly and analysis by year end by FRC.
|  | New Salt Lick (HCVF) | Continuous |  | 0 | 0 |  |  |  |  | No identified new salt lick. (continuously identifed vide CHP planning)
|  | Research | Research on Cats species |  | ongoing | ongoing |  |  |  |  | SFD collaboration with Panthera Maalysia/US. Research. Ongoing.
|  |  | Ecology of Figs to wildlife |  | ongoing | ongoing |  |  |  |  | SFD Colloboration with DR Miyabi of Japan.
|  |  | E-DNA |  | ongoing | ongoing |  |  |  |  | Colloboaration with Dr Hishasi Matsubayasi of Tokyo University.
| ROAD MAINTENANCE | MR 1 | 14km |  | 7 | 14
7 |  | MR 2 | 30km |  | 10 | 30 |  |  |  |  | There is bridge maintenance done at KM27 during this QR.
|  | SR Karis Karis | 9km |  | 13 | 13
|  | SR Anduaus (Balat) | 5KM |  | 0 | 7
|  | SR White House | 8km |  | 0 | 0
|  | SR Heuveldof | 17km |  | 10 | 17
|  | SR Buyung | 6km |  | 0 | 0
|  | SR Kuari | 2km |  | 0 | 2
|  | SR Tabalion | 6km |  | 6 | 6
|  | FR SU | 1.8km |  | 0 | 0
|  | DFR Tower | 1.1km |  | 0 | 1
This is as and when necessary only.
| SOCIAL FORESTRY MEETING | 2x |  |  | 0 | 1 | 0 |  | 1 | 50% | This is not inclusive of 3 direct consultations with the communities.
8 | [10 empty] | Next meeting is scheduled in QR 4
| RESEARCH (PSP PLOTS) | PSP | cpt 18 (9 plots) and 22 (8 plots) |  | 0 | 0 |  |  | 0 | 0% | Yet to be done.
9 | [10 empty] | Will be done by year end (qr 4)
| Capacity Building |  |  |  | 0 | 3 |  |  |  |  | 1/. Roadshows on FSC/Deramakot to Balat and Kuamut communities and DFR personnel. 2/. Baking course at Kuamut. 3/ 2 each of each villages undergone the honorary forest ranger course.
10 | [10 empty] | Expected to be done commencing qr 2.
| UPDATING OF COMPARTMENT RECORD BOOK | 1X |  |  | 0 | 0 |  |  | 0 | 0% | Yet to be done.
Will be done by year end (qr 4)

## tangkulap FMU 17A
QUARTERLY PROGRESS REPORT 2023 (2nd)
TANGKULAP - FMU 17A
NO. | ACTIVITIES | LOCATION / | TARGET |  | ACHIEVEMENT |  |  |  |  | PERCENT | REMARKS
|  | Compt/Block | (ha) | (Species) | QR-1 | QR-2 | QR-3 | QR-4 | TOTAL | (%)
1 | Liberation Treatment | Along KM 25 - 41 of Main Road 1(100m left and right) | 350 |  | 0 | 0 |  |  |  |  | The contract was awarded to Tunas Jaya S/B on 29.05.2023 and is in the documentation process at the moment. Liberation works are to be undertaken during QR 3.
2 | Restoration
| 2.1 Planting | 73 | 34 |  | 0 | 0 |  |  | 0 | 0 | Contract awarded to Permata Paitan s/b on 29.05.2023. Site hand over to be conducted during QR 3.
| 2.2 Maintenance of planted area | 76 | 11ha (2017) | Spot maintenance only (if necessary) | 0 | 0 |  |  | 0 | 0% | No requirement to date
|  | 75 | 36ha (2017) |  | 0 | 0 |  |  | 0 | 0% | No requirement to date.
Individually contracted out to social forestry members of Kg Kenang-Kenangan and Keramuak.
3 | FOREST PROTECTION (As per HCV and protection plan) | A) Patrolling | Ground | at least 200km/month | 1964.45 | 826.5 |  |  | 2790.95 | 116.3% | This is inclusive of weekend patrol. HCV entity of VJR Timbah & water catchment of cpt 22 intact.
|  |  | River | at least 30km/month | 111.24 | 89.34 |  |  | 200.58 | 55.72% | Continuous.
|  |  | Aerial | at least 3x/year | 1 | 1 |  |  | 2 | 66.67% | Along boundary and inland HCV entities. Entities intact.
Entities as per stated in HCV and Protection Plan. Monitoring via ground, river and aerial patrol. Patrolling magnitude as stated above .
|  | B) Boundary Maintenance | 1x/year | 9.6km (cpt 5,6,7,20,23 & 24) | 0 | 0 |  |  | 0 | 0% | To be done by QR 4
|  |  |  | 6.9km (cpt 80 & 90) | 0 | 0 |  |  | 0 | 0% | To be done by QR 4
Workforce will be from Social Forestry Committee of FMU 17A (Kg.Kenang-Kenangan & Keramuak).
4 | WILDLIFE MANAGEMENT | A) Opportunistic Sightings | Continuous |  | continuous | continuous | continuous | continuous |  |  | Daily routine. Compilation/analysis by year end.
|  | B) Orang Utan Census | 1x/year |  | 0 | 0 |  |  | 0 | 0% | To be done in QR 3.
5 | ROAD MAINTENANCE | MR 1 | 26km |  | 35km | 29km |  |  |  |  | Inclusive of a bridge maintenance at KM 37.
|  | SR 1 (Kun Kun) | 10km |  | 10km | 10km
Road will be maintained as and when necessary.
| SOCIAL FORESTRY (FOREST COMMUNITY MEETINGS) | 2x/year |  |  | 0 | 1 |  |  | 1 | 50% | Not including 4 direct consultations at Kg. Keramuak and Tamoi.
6 |  |  |  |  | 1 | 0 | 0 | 1
| RESEARCH | PSP | 9 plots |  | 0 | 0 |  |  | 0 | 0% | To be done in QR 4.
7 | CAPACITY BUILDING |  |  |  | 0 | 1 |  |  |  |  | Honorary Forest Ranger course to 4 Tamoi and 12 Keramuak communities.
8 | UPDATING OF COMPARTMENT RECORD BOOK | 1x |  |  | 0 | 0 |  |  |  |  | Updating by year end.